## Dashboard
Resolution Nation — Roadmap Tracker
Anchored to project start: 2026-06-01
Target: first paying school by ~May 2027 (Month 12).
Phase Summary
Phase | Theme | Tasks | Done | In Progress | Blocked | Not Started | % Done
0 | Foundation & Decisions | 10 | 2 | 0 | 0 | 8 | 20%
1 | Compliance + Hardening | 21 | 4 | 7 | 0 | 10 | 19.05%
2 | School-Ready Features | 18 | 0 | 0 | 0 | 18 | 0%
3 | Mobile Build | 13 | 0 | 0 | 0 | 13 | 0%
4 | Pilot + Certification | 15 | 0 | 0 | 0 | 15 | 0%
5 | App Store Submission | 9 | 0 | 0 | 0 | 9 | 0%
6 | First Paying School | 15 | 0 | 0 | 0 | 15 | 0%
TOTAL |  | 101 | 6 | 7 | 0 | 88 | 5.941%
Key Milestones
Milestone | Target Date | Phase
LLC formed + iKeepSafe intake submitted | 2026-06-15 | 0
Migration 002 in prod (security holes closed) | 2026-07-06 | 1
Legal documents live (privacy, ToS, NY Parent BoR, DPA template) | 2026-08-10 | 1
Google + Sign in with Apple SSO live | 2026-08-24 | 2
Clever Secure Sync certified | 2026-09-28 | 2
First pilot DPA signed | 2026-11-02 | 4
Pilot kickoff (mid-September 2026) | 2026-09-14 | 4
iOS + Android in internal testing | 2026-11-16 | 3
WCAG 2.1 AA audit + remediation done | 2026-11-02 | 2
Pen test report + remediation done | 2026-12-28 | 4
iKeepSafe COPPA cert granted | 2026-12-14 | 4
Apple App Store approval | 2027-03-08 | 5
Google Play approval | 2027-03-08 | 5
First signed paid contract (2027-28 school year) | 2027-04-19 | 6

## Who Does What
Who can do what
Counts pulled by formula from the Roadmap Tasks sheet.
Owner Category | Task Count | What it means
Claude — fully complete | 25 | Claude can do this start to finish. The output is a file in the repo.
Claude (draft) → Attorney | 4 | Claude has drafted; attorney must review before publication.
Claude (draft) → Kaelan | 1 | Claude has drafted; Kaelan needs to finalize, sign, or publish.
Claude + Kaelan | 11 | Claude scaffolds code; Kaelan deploys, integrates, or tests on a device.
Kaelan (Claude: code support) | 5 | Kaelan owns the external setup (Google Cloud, Apple Dev, Clever); Claude can write integration code once configured.
Kaelan only | 33 | Requires Kaelan's accounts, decisions, or vendor relationships. Claude cannot do this.
Kaelan + Attorney | 3 | Requires Kaelan's involvement plus legal review/signature.
External vendor | 1 | Requires a hired vendor (pen test, accessibility audit).
Status counts
Status | Count
Done | 6
In Progress | 7
Blocked | 0
Not Started | 88
Deferred | 0
What Claude completed in this session
RN-8 — Mobile architecture decision (Capacitor) documented in roadmap.
RN-10 — Star Store positioning brief shipped at docs/star-store-positioning.md.
RN-14 — Student parent-invite UI at app/dashboard/student/invite-parent/page.tsx.
RN-15 — Parent redeem UI rewritten at app/parent/link/page.tsx.
RN-16 — Account deletion UI at app/dashboard/settings/delete-account/page.tsx.
RN-17 — Hard-delete cron worker at app/api/cron/hard-delete-accounts/route.ts + vercel.json.
RN-29 — Rate-limit middleware at lib/rate-limit.ts; wired into 3 public routes.
Legal drafts under legal/ (Privacy, ToS, Children's Notice, NY Parent BoR, Sub-processors, DPA checklist).
Migration file at supabase/migrations/002_security_hardening.sql.
Companion API routes for parent-link (code), parent-link (redeem), account deletion.

## Roadmap Tasks
ID | Phase | Category | Task | Owner | Start | Target End | Status | Depends On | Notes
RN-1 | 0 | Legal/Ops | Form Resolution Nation LLC (NY) and register publication | Kaelan | 2026-06-01 | 2026-06-15 | Not Started |  | ~$200 plus NY publication.
RN-2 | 0 | Legal/Ops | Open business bank account (Mercury or local) | Kaelan | 2026-06-01 | 2026-06-15 | Not Started | RN-1
RN-3 | 0 | Legal/Ops | Retain ed-tech attorney (60-min scoping call) | Kaelan | 2026-06-01 | 2026-06-15 | Not Started |  | Find someone with NYC DOE filing experience.
RN-4 | 0 | Infra | Split Supabase: staging-resolutionnation + prod-resolutionnation | Kaelan | 2026-06-01 | 2026-06-08 | Not Started |  | Rotate service-role keys. Enable PITR on prod.
RN-5 | 0 | Infra | GitHub org + branch protection + Dependabot + secret scanning | Kaelan | 2026-06-01 | 2026-06-08 | Not Started
RN-6 | 0 | Infra | Sentry project with PII scrubbing rules | Kaelan (Claude: scrubbing rules) | 2026-06-01 | 2026-06-15 | Not Started |  | Claude can write Sentry beforeSend filters when project exists.
RN-7 | 0 | Compliance | Submit iKeepSafe COPPA Safe Harbor intake questionnaire | Kaelan | 2026-06-01 | 2026-06-08 | Not Started |  | Long lead time; start clock now.
RN-8 | 0 | Product | Decide mobile architecture (Capacitor vs Expo) | Kaelan (Claude: recommendation locked = Capacitor) | 2026-06-08 | 2026-06-22 | Done |  | Decision documented in the production roadmap; Capacitor chosen.
RN-9 | 0 | Compliance | Confirm Supabase region (US East) and Anthropic data terms (zero retention) | Kaelan | 2026-06-01 | 2026-06-15 | Not Started |  | Both go into the sub-processor disclosure.
RN-10 | 0 | Product | Document Star Store positioning: stars are earned, never purchased | Claude | 2026-06-15 | 2026-06-22 | Done |  | Brief shipped at docs/star-store-positioning.md.
RN-11 | 1 | Security | Apply 002_security_hardening.sql migration to staging | Kaelan (Claude: 002_security_hardening.sql ready) | 2026-06-15 | 2026-06-22 | Not Started | RN-4 | Migration file authored by Claude. Kaelan applies to staging.
RN-12 | 1 | Security | Smoke-test new RPCs: award_stars, spend_stars, parent link, deletion | Kaelan | 2026-06-22 | 2026-06-29 | Not Started | RN-11
RN-13 | 1 | Security | Apply 002_security_hardening.sql migration to prod | Kaelan | 2026-06-29 | 2026-07-06 | Not Started | RN-12
RN-14 | 1 | Product | UI for student-generated parent invite code | Claude | 2026-06-22 | 2026-07-06 | Done | RN-12 | Shipped: app/dashboard/student/invite-parent/page.tsx.
RN-15 | 1 | Product | UI for parent enters code to link | Claude | 2026-06-22 | 2026-07-06 | Done | RN-12 | Shipped: app/parent/link/page.tsx (rewritten for code flow).
RN-16 | 1 | Product | UI for account deletion request and cancel (Settings) | Claude | 2026-06-22 | 2026-07-13 | Done | RN-12 | Shipped: app/dashboard/settings/delete-account/page.tsx.
RN-17 | 1 | Product | Scheduled job: hard-delete accounts past 30-day window | Claude | 2026-07-06 | 2026-07-27 | Done | RN-16 | Shipped: app/api/cron/hard-delete-accounts/route.ts + vercel.json cron config.
RN-18 | 1 | Legal | Privacy Policy published (covers FERPA, COPPA, CCPA, Ed Law 2-d) | Claude (draft) → Attorney | 2026-06-15 | 2026-07-13 | In Progress | RN-3 | Draft at legal/privacy-policy.md. Attorney review required.
RN-19 | 1 | Legal | Terms of Service (teacher/school + parent/student) | Claude (draft) → Attorney | 2026-06-15 | 2026-07-13 | In Progress | RN-3 | Draft at legal/terms-of-service.md.
RN-20 | 1 | Legal | Children's Privacy Notice (plain language) | Claude (draft) → Attorney | 2026-06-15 | 2026-07-13 | In Progress | RN-3 | Draft at legal/childrens-privacy-notice.md.
RN-21 | 1 | Legal | NY Parent Bill of Rights for Data Privacy and Security | Claude (draft) → Attorney | 2026-06-15 | 2026-07-13 | In Progress | RN-3 | Draft at legal/ny-parent-bill-of-rights.md.
RN-22 | 1 | Legal | DPA template from SDPC NDPA + NY Exhibit E | Kaelan + Attorney (Claude: checklist) | 2026-06-29 | 2026-08-10 | In Progress | RN-3 | Use SDPC NDPA v1r6 + NY Exhibit E. Pre-execution checklist at legal/dpa-checklist.md.
RN-23 | 1 | Legal | Publish sub-processor list on website | Claude (draft) → Kaelan | 2026-06-22 | 2026-07-13 | In Progress | RN-9 | Draft at legal/subprocessors.md. Add email/push providers once chosen.
RN-24 | 1 | Compliance | Parental consent flow: school-track + direct-to-family-track | Claude + Kaelan | 2026-06-29 | 2026-08-10 | Not Started | RN-18 | Claude can scaffold the consent flow; Kaelan picks the verification method.
RN-25 | 1 | Compliance | Age-gate at signup; route under-13 to parent consent if no school pod | Claude + Kaelan | 2026-06-29 | 2026-08-10 | Not Started | RN-24
RN-26 | 1 | Compliance | Parental data export (JSON download of child's stored data) | Claude + Kaelan | 2026-07-06 | 2026-08-24 | Not Started | RN-24
RN-27 | 1 | Compliance | Data minimization audit (walk every column; drop unneeded fields) | Claude + Kaelan | 2026-06-29 | 2026-07-27 | Not Started
RN-28 | 1 | Security | Encrypt sensitive PII at application layer (names + academic data) | Claude + Kaelan | 2026-07-06 | 2026-08-10 | Not Started |  | Server-side key, quarterly rotation.
RN-29 | 1 | Security | Rate-limit all public API routes | Claude | 2026-06-29 | 2026-07-20 | In Progress |  | Shipped: lib/rate-limit.ts + applied to parent-link, code, account-delete routes. Other API routes still need it.
RN-30 | 1 | Security | Incident response plan + 7-day NY breach notification SOP documented | Claude (draft) + Kaelan | 2026-07-27 | 2026-08-24 | Not Started
RN-31 | 1 | Compliance | Scope a focused web + mobile pen test for late Phase 4 | Kaelan (Claude: code support) | 2026-07-27 | 2026-08-24 | Not Started |  | Needs Google Cloud project + OAuth setup.
RN-32 | 2 | Auth | Google for Education SSO (Supabase Auth Google provider) | Kaelan (Claude: code support) | 2026-07-06 | 2026-08-10 | Not Started | RN-12 | Needs Apple Developer Sign In with Apple service ID.
RN-33 | 2 | Auth | Sign in with Apple | Kaelan (Claude: code support) | 2026-07-20 | 2026-08-24 | Not Started | RN-31 | Needs Microsoft Entra app registration.
RN-34 | 2 | Auth | Microsoft / Entra ID SSO | Kaelan (Claude: code support) | 2026-07-27 | 2026-09-14 | Not Started | RN-31 | Clever app must be registered by Kaelan; Claude can write integration code.
RN-35 | 2 | Rostering | Clever Secure Sync integration (SSO + roster) | Kaelan (Claude: code support) | 2026-07-27 | 2026-09-28 | Not Started | RN-31 | Allow 4-6 weeks for Clever app certification.
RN-36 | 2 | Rostering | ClassLink integration (post-Clever) | Claude | 2026-08-31 | 2026-10-19 | Not Started | RN-34
RN-37 | 2 | Rostering | CSV bulk roster import (fallback for non-Clever schools) | Claude | 2026-07-20 | 2026-08-24 | Not Started
RN-38 | 2 | Product | Teacher dashboard (class mastery, stalled roadmaps, parents linked) | Claude | 2026-07-27 | 2026-09-21 | Not Started
RN-39 | 2 | Product | Bulk student account provisioning (CSV or Clever) | Claude | 2026-08-10 | 2026-09-21 | Not Started | RN-36 | Extend migration 002 pattern; rotate invite_code on use.
RN-40 | 2 | Product | Rotating class invite codes (replace static pod invite_code) | Claude | 2026-07-27 | 2026-08-31 | Not Started
RN-41 | 2 | Product | Teacher-initiated parent invites (inside a class context) | Claude | 2026-07-27 | 2026-08-31 | Not Started | RN-14
RN-42 | 2 | Product | Teacher data export for parent conferences (PDF + CSV) | Claude | 2026-08-24 | 2026-09-28 | Not Started | RN-37
RN-43 | 2 | Product | Student archive flow (end of year) | Claude | 2026-09-14 | 2026-10-19 | Not Started
RN-44 | 2 | Product | Gift-sending guardrails (teacher visibility, optional approval) | External a11y reviewer + Kaelan (Claude: pre-review) | 2026-08-24 | 2026-09-28 | Not Started
RN-45 | 2 | Accessibility | WCAG 2.1 AA audit (color, keyboard, screen-reader, captions, motion) | Claude | 2026-08-31 | 2026-10-19 | Not Started |  | Required by ADA Title II (Apr 2026).
RN-46 | 2 | Accessibility | Remediate WCAG findings | Claude | 2026-09-28 | 2026-11-02 | Not Started | RN-44
RN-47 | 2 | AI | Server-only Anthropic goal-generation pipeline | Claude | 2026-07-27 | 2026-09-14 | Not Started | RN-9 | PII stripped before sending.
RN-48 | 2 | AI | Teacher approval gate before AI goals appear in student roadmaps | Claude | 2026-08-10 | 2026-09-21 | Not Started | RN-46 | Product cannot autonomously assign goals.
RN-49 | 2 | AI | AI call audit log: actor, prompt summary, response summary, cost | Kaelan | 2026-08-10 | 2026-09-21 | Not Started | RN-46 | Surface in district review pack.
RN-50 | 3 | Stores | Apple Developer Program enrollment as LLC ($99/yr) | Kaelan | 2026-06-15 | 2026-07-20 | Not Started | RN-1 | Allow 1-2 weeks entity verification. Start D-U-N-S in parallel.
RN-51 | 3 | Stores | Google Play Console developer account enrollment ($25) | Claude + Kaelan | 2026-06-15 | 2026-07-20 | Not Started | RN-1 | Claude can add Capacitor + config; Kaelan needs Xcode/Android Studio locally.
RN-52 | 3 | Mobile | Add Capacitor to Next.js project; configure ATS for own domains | Claude + Kaelan | 2026-08-03 | 2026-09-14 | Not Started | RN-8 | Claude wires plugins; Kaelan runs on device.
RN-53 | 3 | Mobile | Capacitor plugins: status bar, splash, icons, push, camera, share, in-app browser | Claude + Kaelan | 2026-08-31 | 2026-10-19 | Not Started | RN-51
RN-54 | 3 | Mobile | APNs + FCM push notifications wired end-to-end | Claude + Kaelan | 2026-09-14 | 2026-11-02 | Not Started | RN-52
RN-55 | 3 | Mobile | Universal links / app links for SSO returns | Claude | 2026-08-31 | 2026-10-19 | Not Started | RN-51
RN-56 | 3 | Mobile | Deep links: invite codes open straight to consent flow | Claude | 2026-09-14 | 2026-11-02 | Not Started | RN-51
RN-57 | 3 | Mobile | Offline state for student experience (no blank-screen failures) | Claude | 2026-09-14 | 2026-11-02 | Not Started | RN-51
RN-58 | 3 | Mobile | Remove every 3p SDK that fails Kids Category review | Claude | 2026-09-28 | 2026-11-02 | Not Started | RN-51 | No Facebook, no ad SDKs, no third-party analytics.
RN-59 | 3 | Mobile | Parental gate for any external link or share/rate prompt | Claude (draft) + Kaelan | 2026-09-28 | 2026-11-02 | Not Started | RN-51 | Real math gate, not a dialog.
RN-60 | 3 | Mobile | Privacy nutrition labels + Google Data Safety drafts | Kaelan | 2026-10-19 | 2026-11-16 | Not Started | RN-59 | Requires physical iPad + Kaelan's Apple ID.
RN-61 | 3 | Mobile | iOS build runs on real iPad in TestFlight | Kaelan | 2026-10-19 | 2026-11-16 | Not Started | RN-52 | Requires physical device + Kaelan's Play Console.
RN-62 | 3 | Mobile | Android build runs on Pixel + Chromebook in Internal Testing | Kaelan | 2026-10-19 | 2026-11-16 | Not Started | RN-52
RN-63 | 4 | GTM | Identify 3 pilot teachers from TEP / friendly NY schools | Kaelan + Attorney | 2026-08-10 | 2026-09-28 | Not Started
RN-64 | 4 | Legal | Sign first pilot DPA (SDPC NDPA + NY Exhibit E) | Claude (draft) + Kaelan | 2026-09-28 | 2026-11-02 | Not Started | RN-22, RN-63
RN-65 | 4 | GTM | Pilot agreement (scope, success metrics, feedback cadence) | Kaelan | 2026-09-28 | 2026-11-02 | Not Started | RN-63
RN-66 | 4 | GTM | Pilot kickoff (Monday in mid-September) | Kaelan | 2026-09-14 | 2026-09-28 | Not Started | RN-64, RN-65
RN-67 | 4 | Compliance | iKeepSafe COPPA Safe Harbor — submit application package | Kaelan | 2026-09-14 | 2026-11-02 | Not Started | RN-7, RN-18 | $5k-$10k.
RN-68 | 4 | Compliance | iKeepSafe FERPA certification (bundle with COPPA if possible) | Kaelan + Attorney | 2026-09-14 | 2026-12-14 | Not Started | RN-67
RN-69 | 4 | Compliance | NYC DOE Data Privacy & Security Vendor submission | Claude (draft) + Kaelan | 2026-09-14 | 2026-11-23 | Not Started | RN-22
RN-70 | 4 | Compliance | Common Sense Privacy evaluation submitted | Kaelan | 2026-09-28 | 2026-11-23 | Not Started | RN-18
RN-71 | 4 | Compliance | SDPC directory listing once NDPA signed | External vendor | 2026-11-02 | 2026-12-14 | Not Started | RN-63
RN-72 | 4 | Security | Penetration test commissioned | Claude + Kaelan | 2026-09-28 | 2026-11-23 | Not Started | RN-30 | Triage and remediation; Claude codes fixes once findings come in.
RN-73 | 4 | Security | Pen test findings remediated (high/critical) | Claude (draft) + Kaelan | 2026-11-23 | 2026-12-28 | Not Started | RN-72
RN-74 | 4 | Compliance | Security evidence pack assembled (binder for district CTOs) | Kaelan | 2026-10-19 | 2026-12-14 | Not Started
RN-75 | 4 | Ops | Status page + uptime monitoring with paging | Kaelan | 2026-10-19 | 2026-11-23 | Not Started |  | Better Stack, Statuspage, or instatus.
RN-76 | 4 | Ops | Support inbox with published SLA + auto-reply | Claude (template) + Kaelan | 2026-10-19 | 2026-11-23 | Not Started
RN-77 | 4 | Ops | Public changelog / release notes page | Kaelan | 2026-10-19 | 2026-11-23 | Not Started
RN-78 | 5 | Stores | Apple App Store submission v1.0 | Kaelan | 2026-11-23 | 2026-12-28 | Not Started | RN-59, RN-60 | Expect 1-3 rejection cycles.
RN-79 | 5 | Stores | Respond to Apple review feedback; resubmit as needed | Apple | 2026-12-14 | 2027-02-08 | Not Started | RN-77
RN-80 | 5 | Stores | Apple App Store approval | Kaelan | 2026-12-28 | 2027-03-08 | Not Started | RN-78 | Milestone.
RN-81 | 5 | Stores | Google Play submission v1.0 (Closed → Open → Production) | Kaelan | 2026-11-23 | 2026-12-28 | Not Started | RN-59, RN-61
RN-82 | 5 | Stores | Designed for Families attestation submitted | Kaelan | 2026-11-23 | 2026-12-28 | Not Started | RN-80
RN-83 | 5 | Stores | Respond to Google review feedback; resubmit as needed | Google | 2026-12-14 | 2027-02-08 | Not Started | RN-80
RN-84 | 5 | Stores | Google Play approval | Claude (scaffold) + Kaelan | 2026-12-28 | 2027-03-08 | Not Started | RN-82 | Milestone.
RN-85 | 5 | Ops | Fastlane / EAS automated build pipeline for both stores | Claude (draft) + Kaelan | 2026-11-23 | 2027-01-11 | Not Started | RN-77, RN-80
RN-86 | 5 | Ops | Versioning + rollback runbook | Kaelan | 2026-12-14 | 2027-01-11 | Not Started | RN-84
RN-87 | 6 | GTM | Mid-pilot check-in (month 4 of pilot) | Claude (draft) + Kaelan | 2027-01-11 | 2027-02-01 | Not Started | RN-66
RN-88 | 6 | GTM | Pilot outcome report (anonymized data + stories) | Kaelan | 2027-02-08 | 2027-03-01 | Not Started | RN-86
RN-89 | 6 | GTM | Renewal conversation with pilot school (Feb 2027) | Kaelan | 2027-02-01 | 2027-03-08 | Not Started | RN-87 | Schools budget in spring.
RN-90 | 6 | GTM | Signed annual contract for 2027-28 school year | Kaelan (Claude: runbook) | 2027-03-01 | 2027-04-19 | Not Started | RN-88 | FIRST REVENUE.
RN-91 | 6 | Ops | Backup/restore drill #1 | Kaelan (Claude: runbook) | 2026-12-14 | 2027-01-11 | Not Started |  | Quarterly thereafter.
RN-92 | 6 | Ops | Key rotation calendar set up (service-role quarterly) | Claude (drafts) + Kaelan | 2026-12-14 | 2027-01-11 | Not Started |  | Claude can draft all help articles.
RN-93 | 6 | Ops | Help center: 20-30 short articles + Loom videos | Kaelan | 2026-12-14 | 2027-03-08 | Not Started
RN-94 | 6 | Ops | Monthly check-in with pilot lead teacher + principal | Kaelan | 2026-11-02 | 2027-06-01 | Not Started | RN-66
RN-95 | 6 | Compliance | Decide SOC 2 path (Type I now or Type II in Year 2) | Kaelan | 2027-02-01 | 2027-03-08 | Not Started
RN-96 | 6 | Compliance | Choose compliance automation tool (Vanta / Drata / Secureframe) | Claude | 2026-12-14 | 2027-02-01 | Not Started | RN-94
RN-97 | 6 | Tech Debt | Move PDF/CSV processing into a queued worker | Claude | 2027-02-08 | 2027-04-19 | Not Started | RN-48
RN-98 | 6 | Tech Debt | Materialized views for teacher dashboards | Claude | 2027-02-08 | 2027-04-19 | Not Started | RN-37
RN-99 | 6 | Tech Debt | Split service-role surface; prefer RPCs over admin client | Claude + Kaelan | 2027-02-08 | 2027-04-19 | Not Started
RN-100 | 6 | Product | Localization scaffolding (English; Spanish next) | Kaelan | 2027-03-08 | 2027-06-01 | Not Started
RN-101 | 6 | Insurance | Cyber liability insurance ($1M, ~$1-3k/yr) before first paid contract | Kaelan | 2027-02-08 | 2027-03-08 | Not Started

## Compliance
Artifact / Cert | Authority | Required For | Target Date | Status | Cost (est.) | Owner | Evidence Location | Notes
Privacy Policy | Self-published | All school sales | 2026-07-13 | Not Started | $1-3k legal | Attorney + Kaelan | /legal/privacy | Covers FERPA, COPPA, CCPA, NY Ed Law 2-d.
Terms of Service | Self-published | All users | 2026-07-13 | Not Started | $1-3k legal | Attorney + Kaelan | /legal/terms | Separate teacher/school + parent/student.
Children's Privacy Notice | Self-published | Schools + parents | 2026-07-13 | Not Started | Included in legal | Attorney + Kaelan | /legal/childrens-privacy
NY Parent Bill of Rights | NYSED | Any NY school | 2026-07-13 | Not Started | Template | Attorney + Kaelan | /legal/ny-parent-bill | Ed Law 2-d §121.3.
DPA template (SDPC NDPA + NY Exhibit E) | SDPC + NYSED | Every NY contract | 2026-08-10 | Not Started | Attorney review $2-5k | Attorney + Kaelan | /legal/dpa
Sub-processor list (Supabase, Vercel, Anthropic, Sentry...) | Self-published | All districts | 2026-07-13 | Not Started | — | Kaelan | /legal/subprocessors
Parental consent flow (in-product) | COPPA | Direct-to-family signups | 2026-08-10 | Not Started | Engineering time | Kaelan | Product: signup
Audit log (in-product) | FERPA / Ed Law 2-d | All districts | 2026-07-06 | Not Started | Engineering time | Kaelan | DB: audit_log | Shipped in migration 002.
Account deletion (in-product) | Apple / Google / FERPA | App Store + district reviews | 2026-07-13 | Not Started | Engineering time | Kaelan | Settings → Delete account | Shipped in migration 002 + /api/account/delete.
Data export (parental access) | FERPA / Ed Law 2-d | Districts + parents | 2026-08-24 | Not Started | Engineering time | Kaelan | Settings → Export my data
Incident response plan | Ed Law 2-d | All NY districts | 2026-08-24 | Not Started | Template | Kaelan | Internal runbook | 7-day NY breach notification.
Penetration test report | Best practice + DPA asks | Districts + iKeepSafe | 2026-12-28 | Not Started | $5-15k | External vendor | Internal
iKeepSafe COPPA Safe Harbor certification | iKeepSafe | All districts | 2026-11-02 | Not Started | $5-10k | Kaelan | Cert page | Submit intake Phase 0.
iKeepSafe FERPA certification | iKeepSafe | All districts | 2026-12-14 | Not Started | $5-10k | Kaelan | Cert page | Bundle with COPPA if possible.
NYC DOE Data Privacy submission | NYC DOE | Any NYC public school | 2026-11-23 | Not Started | $500-1.5k attorney | Kaelan + Attorney | DOE portal | VendorHotline@schools.nyc.gov.
Common Sense Privacy evaluation | Common Sense | Parents + districts | 2026-11-23 | Not Started | Free | Kaelan | commonsense.org listing
SDPC directory listing | SDPC | All districts | 2026-12-14 | Not Started | Free | Kaelan | sdpc.a4l.org | Requires signed NDPA first.
VPAT (WCAG 2.1 AA conformance statement) | Self-attested | Districts + ADA | 2026-11-02 | Not Started | $2-5k consultant | Kaelan + a11y reviewer | /legal/vpat
Cyber liability insurance ($1M) | Insurance market | Before first paid contract | 2027-03-08 | Not Started | $1-3k/yr | Kaelan | Policy on file | Required by many districts.
SOC 2 Type I (optional Year 1) | AICPA | Larger districts | 2027-04-19 | Not Started | $15-30k | Kaelan | Auditor report | Type II in Year 2.

## App Store
Store | Category | Requirement | Status | Notes
Apple | Account | Apple Developer Program enrolled as LLC | Not Started | $99/yr.
Apple | Account | D-U-N-S number obtained | Not Started | Free; can take weeks.
Apple | Account | Two App Store Connect users (primary + backup) | Not Started | Avoid single-account lockout.
Apple | Submission | Privacy nutrition labels match code reality | Not Started
Apple | Submission | Demo account credentials (sandbox, not a real teacher) | Not Started
Apple | Submission | App Review notes explaining school context + parental consent | Not Started | Reviewers aren't edtech specialists.
Apple | Required Feature | In-app account deletion (Guideline 5.1.1(v)) | Not Started | Shipped in /api/account/delete.
Apple | Required Feature | Sign in with Apple offered (if any 3p login present) | Not Started
Apple | Kids Category | No third-party analytics SDKs | Not Started
Apple | Kids Category | No behavioral advertising; declare zero tracking | Not Started
Apple | Kids Category | Parental gate for all external links / rate prompts | Not Started | Real math gate.
Apple | Kids Category | Decide: opt into Kids Category (yes/no) | Not Started | Credibility vs. extra rules.
Apple | Build | Capacitor build runs on real iPad via TestFlight | Not Started
Apple | Assets | App icons (all sizes) | Not Started
Apple | Assets | Screenshots (6.7", 6.5", 5.5", iPad 12.9") | Not Started
Apple | Assets | Promotional text + description copy | Not Started
Apple | Pipeline | Fastlane / EAS automated build | Not Started
Apple | Pipeline | Phased Release configured | Not Started
Google | Account | Play Console developer account enrolled as LLC | Not Started | $25 one-time.
Google | Account | Identity verification complete | Not Started | Required under EU rules.
Google | Submission | Data Safety form matches code reality | Not Started | Google audits this aggressively.
Google | Submission | Target SDK level current (raised every August) | Not Started
Google | Submission | App Bundle (.aab) not APK | Not Started
Google | Submission | 64-bit support | Not Started
Google | Required Feature | In-app account deletion path (User Data policy) | Not Started | Shipped in /api/account/delete.
Google | Families | Designed for Families opt-in submitted | Not Started
Google | Families | No third-party ad SDKs | Not Started
Google | Families | No behavioral analytics | Not Started
Google | Families | Age-appropriate content rating | Not Started
Google | Build | Capacitor build runs on Pixel + Chromebook (Android container) | Not Started
Google | Assets | App icon + feature graphic | Not Started
Google | Assets | Screenshots (phone + tablet) | Not Started
Google | Assets | Store listing copy | Not Started
Google | Pipeline | Closed → Open → Production rollout tracks configured | Not Started

## Risks
# | Risk | Likelihood | Impact | Mitigation | Owner | Status | Review By
R-1 | Founder burnout (solo + full-time teaching) | High | Severe | Schedule summer build sprints + part-time sabbatical. Hire contract help by Month 9-12. Aggressive scope discipline. | Kaelan | Open | 2026-11-28
R-2 | App Store rejection (Kids Category) delays pilot launch | Medium | Severe | Design Kids Category compliance into Phase 3, not retrofit. Submit early TestFlight to surface issues. | Kaelan | Open | 2026-11-28
R-3 | iKeepSafe / NYC DOE certification slower than planned | High | Moderate | Submit intake in Phase 0/1, not Phase 4. Pilot can proceed on signed DPA before cert completes. | Kaelan | Open | 2026-09-29
R-4 | Serious finding during pen test | Medium | High | Pen test before pilot expansion not before pilot start. Budget 2-3 weeks remediation. Vendor that includes remediation guidance. | Kaelan | Open | 2026-12-28
R-5 | COPPA complaint filed with FTC | Low | Severe | iKeepSafe Safe Harbor resolution path. Robust consent + audit log makes most complaints resolvable in writing. | Kaelan + Attorney | Open | 2026-11-28
R-6 | AI costs scale faster than revenue | Medium | Moderate | Cache aggressively. Haiku for classification, Sonnet only for goal generation. Cap unit economics at $1-$2/student/year. | Kaelan | Open | 2026-09-29
R-7 | Vendor questionnaire fatigue (5+ schools at once) | High (after M8) | Moderate | Pre-fill CASBO, NDPA Exhibit E, K-12 SIX. Single source-of-truth questionnaire bank. | Kaelan | Open | 2027-01-27
R-8 | Apple or Google policy change mid-build | Medium | Moderate | Subscribe to platform developer news. Re-audit privacy declarations before every submission. | Kaelan | Open | 2026-10-29
R-9 | Pilot teacher churns or moves before conversion | Medium | High | Pilot with at least 2 teachers. Maintain principal relationship in parallel. | Kaelan | Open | 2026-12-28
R-10 | Data breach | Low | Severe | Layered controls: encryption, RLS, audit log, pen test, IR plan. Cyber liability insurance before first paid contract. | Kaelan | Open | 2027-02-26

## How to Use
Resolution Nation — Roadmap Tracker
How to use this workbook
1. The Dashboard sheet is the at-a-glance view. Phase counts update automatically from the Roadmap Tasks sheet.
2. Roadmap Tasks is the primary work surface. Status options are: Not Started, In Progress, Blocked, Done, Deferred. Colors are applied automatically.
3. The Compliance sheet tracks every legal artifact and certification with target dates.
4. The App Store sheet is the pre-submission checklist for Apple and Google. Work through it before each store submission.
5. The Risks sheet is reviewed monthly. Update the Review By date and the Status as risks change.
Dates
All target dates are anchored to a project start of 2026-06-01. If the start slips, the cleanest approach is to shift every date by the same offset; do not recompute task-by-task.
Phase color legend
Phase 0 — Foundation & Decisions
Phase 1 — Compliance + Hardening
Phase 2 — School-Ready Features
Phase 3 — Mobile Build
Phase 4 — Pilot + Certification
Phase 5 — App Store Submission
Phase 6 — First Paying School
Companion documents
Resolution_Nation_Production_Roadmap.docx — narrative roadmap with rationale and exit criteria.
Resolution_Nation_GTM_Strategy.docx — market sizing, pricing, sales motion.
CHANGES.md — security fixes applied 2026-05-25.
The one rule
Compliance work is the critical path to revenue. Phase 1 in green > Phase 1 behind > everything else.